## Master_Data
Record_ID | Record_Type | Bank_ID | Bank_Entity_EN | Bank_Entity_AR | Product_Code | Category_Stage | Status | Progress_% | Date_Value | Date_Type | Responsible_Person | Priority_Impact | Description_Notes | Reference_Link | Last_Updated | Risk_Level | Next_Meeting_Date | Next_Meeting_Topic | Last_Meeting_Summary | Next_Action | Executive_Summary | Hero_Image_URL | Logo_URL
BANK-001 | Bank/Entity | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | Local Bank | Active - Integration In Progress |  | 2026-02-19 | Last Meeting/Contact Date | Mustafa Al-Awami; Badr Al-Sahli | HOT | Financing types: Tenant;Landlord;Off-plan;Self-build;SME;Ready-units. Contact: Saud Bajbeer (VP, +966562004300). Pipeline: Initial Contact, Presentation, Demo, NDA done; Integration & Negotiation PENDING. Tenant financing: meeting targeted before Ramadan. Off-plan financing: SNB sent required technical-integration linkage email on Mon 16 Feb. | https://www.snb.com.sa | 2026-07-08 | High | Not Scheduled | - | 2026-02-16 - Technical integration linkage requirements: SNB sent required technical linkage email. | Partner Follow-up: Follow up on Business Analysis for E1 (Tenant Financing (E1)) (Due: 2026-05-30) | Saudi National Bank (SNB) (Local Bank) is a active - integration in progress partner. 2 active integration product(s) averaging 30% complete. Current stage: S3: Business Analysis (40%) ¦ E1: Business Analysis (20%). Risk level: High. Relationship classified HOT. Next step: Partner Follow-up: Follow up on Business Analysis for E1 (Tenant Financing (E1)) (Due: 2026-05-30) | https://placehold.co/1600x500/1E2761/FFFFFF?text=Saudi+National+Bank+(SNB) | https://logo.clearbit.com/snb.com.sa
BANK-002 | Bank/Entity | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Local Bank | Active - Integration In Progress |  | 2026-02-19 | Last Meeting/Contact Date | Ismail Al-Qahtani; Majed Al-Omran | HOT | Financing types: Tenant;Landlord;Off-plan;Self-build;SME;Ready-units. Contact: Sultan Alsabban (Project Management, +966545402013). Pipeline: Initial Contact, Presentation, Demo, NDA done; Integration & Negotiation PENDING. Followed up on NOC request status (Tue 10 Feb); bank to confirm same day. Meeting held Thu 12 Feb. Off-plan product concept presented Wed 18 Feb. | https://www.alrajhibank.com.sa | 2026-07-08 | High | Not Scheduled | - | 2026-07-07 - Requirements analysis meeting: Held at the bank. | Partner Follow-up: Follow up on Agreement / Business Analysis for S3 (Product S3) (Due: 2026-04-30) | Al Rajhi Bank (Local Bank) is a active - integration in progress partner. 2 active integration product(s) averaging 40% complete. Current stage: E1: Testing / Obtaining NOC (blocked) (60%) ¦ S3: Agreement / Business Analysis (20%). Risk level: High. Relationship classified HOT. Next step: Partner Follow-up: Follow up on Agreement / Business Analysis for S3 (Product S3) (Due: 2026-04-30) | https://placehold.co/1600x500/1E2761/FFFFFF?text=Al+Rajhi+Bank | https://logo.clearbit.com/alrajhibank.com.sa
BANK-003 | Bank/Entity | BANK-003 | Riyad Bank | بنك الرياض | - | Local Bank | Active - Integration In Progress |  | 2026-02-19 | Last Meeting/Contact Date | Mustafa Al-Awami | HOT | Financing types: Tenant;Landlord;Off-plan;Self-build;SME;Ready-units. Contact: Waleed Aldawsri (Digital Director, +966553122440). Pipeline: Initial Contact, Presentation, Demo, NDA, Integration, Negotiation all Y (most advanced pipeline). Attempted call 10 Feb (no answer); meeting rescheduled for Thursday to cover product E1. | https://www.riyadbank.com | 2026-07-08 | High | Not Scheduled | - | 2026-02-12 - Product E1 status review: Rescheduled from failed call attempt on 10 Feb. | Partner Follow-up: Follow up on Obtaining NOC / Change Request Development (blocked) for E1 (Tenant Financing (E1)) (Due: TBD) | Riyad Bank (Local Bank) is a active - integration in progress partner. 1 active integration product(s) averaging 70% complete. Current stage: E1: Obtaining NOC / Change Request Development (blocked) (70%). Risk level: High. Relationship classified HOT. Next step: Partner Follow-up: Follow up on Obtaining NOC / Change Request Development (blocked) for E1 (Tenant Financing (E1)) (Due: TBD) | https://placehold.co/1600x500/1E2761/FFFFFF?text=Riyad+Bank | https://logo.clearbit.com/riyadbank.com
BANK-004 | Bank/Entity | BANK-004 | Banque Saudi Fransi (BSF) | البنك السعودي الفرنسي | - | Local Bank | Prospecting - Engaged |  | 2026-02-19 | Last Meeting/Contact Date | Ismail Abdulelah | Unclassified | Financing types: Tenant;Landlord;Off-plan;Ready-units. Contact: Norah Alajlan (Retail Banking - Personal Finance Business, +966505268370). Pipeline: Initial Contact, Presentation, Demo, NDA done; Integration not started. Contacted re: platform concept; bank showed initial interest and requested a company profile deck (Wasl profile being refreshed - awaiting final version). | https://www.alfransi.com | 2026-07-08 | Not Rated | Not Scheduled | - | 2026-02-19 - Status update logged (no structured meeting record). | No open action - monitor relationship for new opportunities. | Banque Saudi Fransi (BSF) (Local Bank) is a prospecting - engaged partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Banque+Saudi+Fransi+(BSF) | https://logo.clearbit.com/alfransi.com
BANK-005 | Bank/Entity | BANK-005 | Alinma Bank | مصرف الإنماء | - | Local Bank | Active - Integration In Progress |  | 2026-02-19 | Last Meeting/Contact Date | Mustafa Al-Awami | HOT | Financing types: Tenant;Landlord;Off-plan;SME;Ready-units. Contact: Latifah Albatili (Real Estate Business Development, +966544220060). Pipeline: Initial Contact, Presentation, Demo, NDA done; Integration & Negotiation PENDING. Tenant-financing meeting held Tue 17 Feb to walk through technical integration document. Off-plan: no answer Mon 9 Feb, meeting rescheduled Tue 10 Feb. | https://www.alinma.com | 2026-07-08 | High | Not Scheduled | - | 2026-02-17 - Walkthrough of technical integration document: Held Tuesday 17 Feb. | No open action - monitor relationship for new opportunities. | Alinma Bank (Local Bank) is a active - integration in progress partner. 2 active integration product(s) averaging 12% complete. Current stage: S3: Agreement (20%) ¦ E1: Agreement (5%). Risk level: High. Relationship classified HOT. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Alinma+Bank | https://logo.clearbit.com/alinma.com
BANK-006 | Bank/Entity | BANK-006 | Saudi Awwal Bank (SAB) | البنك السعودي الأول (ساب) | - | Local Bank | Prospecting - Engaged |  | 2026-02-19 | Last Meeting/Contact Date | Ismail | Unclassified | Financing types: Tenant;Landlord;Off-plan;SME;Ready-units. Contact: Sultan Alshammari (VP of Mortgage, +966552482190). Pipeline: Initial Contact, Presentation, Demo done; NDA PENDING. Follow-up email sent 18 Feb to schedule meetings for both off-plan and tenant-financing products. | https://www.sab.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | 2026-02-18 - Meeting scheduling for both products: Awaiting bank response. | No open action - monitor relationship for new opportunities. | Saudi Awwal Bank (SAB) (Local Bank) is a prospecting - engaged partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Saudi+Awwal+Bank+(SAB) | https://logo.clearbit.com/sab.com.sa
BANK-007 | Bank/Entity | BANK-007 | Albilad Bank | بنك البلاد | - | Local Bank | Contacted - No Update |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Off-plan;Tenant;Landlord;Ready-units. Contact: Not yet identified (-, -). Pipeline: Not started. No update on record. | https://www.bankalbilad.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Albilad Bank (Local Bank) is a contacted - no update partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Albilad+Bank | https://logo.clearbit.com/bankalbilad.com.sa
BANK-008 | Bank/Entity | BANK-008 | Aljazira Bank | بنك الجزيرة | - | Local Bank | Prospecting - Engaged |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Tenant;Landlord;SME;Ready-units. Contact: Unknown (-, +966552678080). Pipeline: Not started. No update on record. | https://www.bankaljazira.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Aljazira Bank (Local Bank) is a prospecting - engaged partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Aljazira+Bank | https://logo.clearbit.com/bankaljazira.com.sa
BANK-009 | Bank/Entity | BANK-009 | Arab National Bank (ANB) | البنك العربي الوطني | - | Local Bank | Active - Integration In Progress |  | 2026-01-19 | Last Meeting/Contact Date | Mustafa Al-Awami | Unclassified | Financing types: Tenant;Landlord;SME;Ready-units. Contact: Madhawi Alsubie (Real Estate Business Development, +966574147410). Pipeline: Initial Contact, Presentation, Demo done; NDA PENDING. Bank is pursuing its own NOC before starting technical integration for tenant financing; Wasl pushing to run integration in parallel with the NOC process. | https://www.anb.com.sa | 2026-07-08 | High | Not Scheduled | - | 2026-01-19 - NOC & integration sequencing: Bank pursuing NOC in parallel track. | No open action - monitor relationship for new opportunities. | Arab National Bank (ANB) (Local Bank) is a active - integration in progress partner. 1 active integration product(s) averaging 20% complete. Current stage: E1: Technical Development (pending internal coordination) (20%). Risk level: High. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Arab+National+Bank+(ANB) | https://logo.clearbit.com/anb.com.sa
BANK-010 | Bank/Entity | BANK-010 | Gulf International Bank (GIB) | بنك الخليج الدولي | - | Local Bank | Contacted - No Update |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: SME;Corporate. Contact: Not yet identified (-, -). Pipeline: Not started. No update on record. | https://www.gibl.com | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Gulf International Bank (GIB) (Local Bank) is a contacted - no update partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Gulf+International+Bank+(GIB) | https://logo.clearbit.com/gibl.com
BANK-011 | Bank/Entity | BANK-011 | STC Bank | بنك STC | - | Digital Bank (licensed) | Active - Integration In Progress |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Consumer. Contact: Abdulaziz Al-Ghazi (-, +966300009510). Pipeline: Not started. No update on record. | https://www.stcbank.com.sa | 2026-07-08 | High | Not Scheduled | - | No meetings on record. | Partner Follow-up: Follow up on Opportunity Study & Bank Presentation for E1 (Tenant Financing (E1)) (Due: 2026-05-30) | STC Bank (Digital Bank (licensed)) is a active - integration in progress partner. 1 active integration product(s) averaging 10% complete. Current stage: E1: Opportunity Study & Bank Presentation (10%). Risk level: High. Next step: Partner Follow-up: Follow up on Opportunity Study & Bank Presentation for E1 (Tenant Financing (E1)) (Due: 2026-05-30) | https://placehold.co/1600x500/1E2761/FFFFFF?text=STC+Bank | https://logo.clearbit.com/stcbank.com.sa
BANK-012 | Bank/Entity | BANK-012 | D360 Bank | D360 Bank | - | Digital Bank | Active - Integration In Progress |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Consumer. Contact: Not yet identified (-, -). Pipeline: Not started. No update on record. | https://www.d360bank.com | 2026-07-08 | Medium | Not Scheduled | - | No meetings on record. | Partner Follow-up: Follow up on Opportunity Study & Bank Presentation for E1 (Tenant Financing (E1)) (Due: 2026-07-15) | D360 Bank (Digital Bank) is a active - integration in progress partner. 1 active integration product(s) averaging 5% complete. Current stage: E1: Opportunity Study & Bank Presentation (5%). Risk level: Medium. Next step: Partner Follow-up: Follow up on Opportunity Study & Bank Presentation for E1 (Tenant Financing (E1)) (Due: 2026-07-15) | https://placehold.co/1600x500/1E2761/FFFFFF?text=D360+Bank | https://logo.clearbit.com/d360bank.com
BANK-013 | Bank/Entity | BANK-013 | Saudi Finance Company (SFC) | الشركة السعودية للتمويل | - | Licensed Finance Company | Contacted - No Update |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: SME;Consumer;Mortgage-backed. Contact: Not yet identified (-, -). Pipeline: Not started. No update on record. | https://sfco.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Saudi Finance Company (SFC) (Licensed Finance Company) is a contacted - no update partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Saudi+Finance+Company+(SFC) | https://logo.clearbit.com/sfco.com.sa
BANK-014 | Bank/Entity | BANK-014 | Abdul Latif Jameel Finance | عبد اللطيف جميل للتمويل | - | Finance Company | Contacted - No Update |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Mortgage;SME;Consumer. Contact: Not yet identified (-, -). Pipeline: Not started. No update on record. | https://www.alj.com | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Abdul Latif Jameel Finance (Finance Company) is a contacted - no update partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Abdul+Latif+Jameel+Finance | https://logo.clearbit.com/alj.com
BANK-015 | Bank/Entity | BANK-015 | Bidaya Finance | بداية للتمويل | - | Finance Company | Prospecting - Engaged |  | 2026-02-02 | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Mortgage;Off-plan;Ready-units. Contact: Rawad Zarea (Product Director, +966553400020). Pipeline: Initial Contact, Presentation, Demo, NDA done. No status update on record. | https://www.bidaya.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | 2026-02-02 - Relationship status check-in: - | No open action - monitor relationship for new opportunities. | Bidaya Finance (Finance Company) is a prospecting - engaged partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Bidaya+Finance | https://logo.clearbit.com/bidaya.com.sa
BANK-016 | Bank/Entity | BANK-016 | Nayifat | نايفات | - | Real Estate Finance Company | Active - Integration Complete |  | 2026-01-28 | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Mortgage;Off-plan;Ready-units. Contact: Not yet identified (-, -). Pipeline: Not started. In progress - Tenant financing E1 (see Products Matrix for stage detail). | https://nayifat.com.sa | 2026-07-08 | Low | Not Scheduled | - | 2026-01-28 - Integration progress check-in: - | No open action - monitor relationship for new opportunities. | Nayifat (Real Estate Finance Company) is a active - integration complete partner. 1 active integration product(s) averaging 100% complete. Current stage: E1: Fully Complete - NOC Obtained (100%). Risk level: Low. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Nayifat | https://logo.clearbit.com/nayifat.com.sa
BANK-017 | Bank/Entity | BANK-017 | Yanal | يانال | - | Finance Company | Not Yet Contacted |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: SME;Equipment;Asset finance. Contact: Not yet identified (-, -). Pipeline: Not started. Not yet contacted. | https://www.saudi-orix.com | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Yanal (Finance Company) is a not yet contacted partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Yanal | https://logo.clearbit.com/saudi-orix.com
BANK-018 | Bank/Entity | BANK-018 | Al Yusr | اليسر للتمويل | - | Finance Company | Inactive - Stopped/Unresponsive |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Consumer;SME;Mortgage-related products. Contact: Nuha (Project Manager, +966552044440). Pipeline: Initial Contact, Presentation, Demo, NDA done. Unresponsive - Tenant financing E1. | https://www.alyusr.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Al Yusr (Finance Company) is a inactive - stopped/unresponsive partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Al+Yusr | https://logo.clearbit.com/alyusr.com.sa
BANK-019 | Bank/Entity | BANK-019 | AJIL Financial Services | أجل للخدمات المالية | - | Finance Company | Not Yet Contacted |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Consumer;SME. Contact: Not yet identified (-, -). Pipeline: Not started. Not yet contacted. | https://ajil.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | AJIL Financial Services (Finance Company) is a not yet contacted partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=AJIL+Financial+Services | https://logo.clearbit.com/ajil.com.sa
BANK-020 | Bank/Entity | BANK-020 | Kirnaf Finance | كِرنف للتمويل | - | Finance Company | Not Yet Contacted |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Mortgage;Consumer. Contact: Not yet identified (-, -). Pipeline: Not started. Not yet contacted. | https://www.kirnaf.com | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Kirnaf Finance (Finance Company) is a not yet contacted partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Kirnaf+Finance | https://logo.clearbit.com/kirnaf.com
BANK-021 | Bank/Entity | BANK-021 | Matager | مطاجر | - | Finance Company | Not Yet Contacted |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Mortgage;Off-plan. Contact: Not yet identified (-, -). Pipeline: Not started. Not yet contacted. | https://www.matager.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Matager (Finance Company) is a not yet contacted partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Matager | https://logo.clearbit.com/matager.sa
BANK-022 | Bank/Entity | BANK-022 | Saudi Real Estate Refinance Co. (SRC) | شركة التمويل العقاري السعودية | - | Refinance Company | Not Yet Contacted |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Mortgage-refinance. Contact: Not yet identified (-, -). Pipeline: Not started. Not yet contacted. | https://www.src.com.sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Saudi Real Estate Refinance Co. (SRC) (Refinance Company) is a not yet contacted partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Saudi+Real+Estate+Refinance+Co.+(SRC) | https://logo.clearbit.com/src.com.sa
BANK-023 | Bank/Entity | BANK-023 | J-B Finance | جيبي | - | Finance Company | Active - Integration In Progress |  | 2026-02-19 | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: SME;Consumer;Mortgage-backed. Contact: Not yet identified (-, -). Pipeline: Not started. Followed up regarding completion of trial phase (Mon 16 Feb). | https://j-b.com.sa/en/ | 2026-07-08 | Medium | Not Scheduled | - | 2026-02-16 - Trial-phase completion follow-up: - | No open action - monitor relationship for new opportunities. | J-B Finance (Finance Company) is a active - integration in progress partner. 1 active integration product(s) averaging 95% complete. Current stage: E1: Testing (الاختبارات) (95%). Risk level: Medium. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=J-B+Finance | https://logo.clearbit.com/j-b.com.sa
BANK-024 | Bank/Entity | BANK-024 | The Saudi Investment Bank | البنك السعودي للإستثمار | - | Local Bank | Prospecting - Engaged |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Tenant;Landlord;Off-plan;Self-build;SME;Ready-units. Contact: Adel Alsugair (Mortgage Manager, +966550038400). Pipeline: Initial Contact, Presentation, Demo done; NDA PENDING. Contacted Sultan Al-Khamis; company profile to be emailed, then NDA status to be checked. | https://www.saib.com.sa/ar | 2026-07-08 | Not Rated | Not Scheduled | - | 2026-02-19 - Company profile & NDA status: Profile to be emailed; NDA status to be checked next. | No open action - monitor relationship for new opportunities. | The Saudi Investment Bank (Local Bank) is a prospecting - engaged partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=The+Saudi+Investment+Bank | https://logo.clearbit.com/saib.com.sa
BANK-025 | Bank/Entity | BANK-025 | Tamara | تمارا | - | Buy Now Pay Later | Inactive - Stopped/Unresponsive |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Consumer. Contact: Not yet identified (-, -). Pipeline: Not started. Stopped - Tenant financing E1. | https://tamara.co/ar-sa | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Tamara (Buy Now Pay Later) is a inactive - stopped/unresponsive partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Tamara | https://logo.clearbit.com/tamara.co
BANK-026 | Bank/Entity | BANK-026 | Emkan | إمكان | - | Finance Company | Inactive - Stopped/Unresponsive |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Consumer. Contact: Fahad Alhindi / Hazim Turkistani (Project Manager, +966555547120 / +966571234710). Pipeline: Not started. Stopped - Tenant financing E1. | https://www.emkanfinance.com.sa/ | 2026-07-08 | Not Rated | Not Scheduled | - | No meetings on record. | No open action - monitor relationship for new opportunities. | Emkan (Finance Company) is a inactive - stopped/unresponsive partner. No active integration product currently underway. Current stage: No Active Integration. Risk level: Not Rated. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Emkan | https://logo.clearbit.com/emkanfinance.com.sa
BANK-027 | Bank/Entity | BANK-027 | Raize | رايز | - | Finance Company | Active - Integration In Progress |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Not specified. Contact: Not yet identified (-, -). Pipeline: Not started. No contact-tracker record; sourced from integration status deck only. | Not available | 2026-07-08 | High | Not Scheduled | - | No meetings on record. | Partner Follow-up: Follow up on Agreement for E1 (Tenant Financing (E1)) (Due: 2026-04-30) | Raize (Finance Company) is a active - integration in progress partner. 1 active integration product(s) averaging 5% complete. Current stage: E1: Agreement (5%). Risk level: High. Next step: Partner Follow-up: Follow up on Agreement for E1 (Tenant Financing (E1)) (Due: 2026-04-30) | https://placehold.co/1600x500/1E2761/FFFFFF?text=Raize | Not available - add manually
BANK-028 | Bank/Entity | BANK-028 | Manafea | منافع | - | Financing Entity | Active - Integration In Progress |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Not specified. Contact: Not yet identified (-, -). Pipeline: Not started. No contact-tracker record; sourced from integration status deck only. | Not available | 2026-07-08 | Medium | 2026-07-15 | Requirements analysis meeting (Meeting (Planned)) | No meetings on record. | No open action - monitor relationship for new opportunities. | Manafea (Financing Entity) is a active - integration in progress partner. 1 active integration product(s) averaging 10% complete. Current stage: E2: Agreement / Business Analysis (10%). Risk level: Medium. Next step: No open action - monitor relationship for new opportunities. | https://placehold.co/1600x500/1E2761/FFFFFF?text=Manafea | Not available - add manually
BANK-029 | Bank/Entity | BANK-029 | Barq | برق | - | Financing Entity | Not Yet Contacted |  |  | Last Meeting/Contact Date | Wasl Partnerships Team | Unclassified | Financing types: Not specified. Contact: Not yet identified (-, -). Pipeline: Not started. No contact-tracker record; sourced from integration status deck only. | Not available | 2026-07-08 | Medium | Not Scheduled | - | No meetings on record. | Partner Follow-up: Follow up on Opportunity Study & Presentation to Financing Entity for E1 (Tenant Financing (E1)) (Due: TBD) | Barq (Financing Entity) is a not yet contacted partner. 1 active integration product(s) averaging 0% complete. Current stage: E1: Opportunity Study & Presentation to Financing Entity (0%). Risk level: Medium. Next step: Partner Follow-up: Follow up on Opportunity Study & Presentation to Financing Entity for E1 (Tenant Financing (E1)) (Due: TBD) | https://placehold.co/1600x500/1E2761/FFFFFF?text=Barq | Not available - add manually
PRD-001 | Product/Integration | BANK-023 | J-B Finance | جيبي | E1 | Testing (الاختبارات) | In Progress | 95% | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Tenant Financing (E1). Required approvals: -. Upcoming: Testing. NOC obtained for J-B. Business analysis & technical development complete; testing in progress. | - | 2026-07-08 | Medium
PRD-002 | Product/Integration | BANK-016 | Nayifat | نايفات | E1 | Fully Complete - NOC Obtained | Complete | 100% | 2026-06-23 | Target Date | Wasl Partnerships Team | - | Tenant Financing (E1). Required approvals: -. Upcoming: None - Complete. All stages complete; Nayifat obtained the NOC. | - | 2026-07-08 | Low
PRD-003 | Product/Integration | BANK-003 | Riyad Bank | بنك الرياض | E1 | Obtaining NOC / Change Request Development (blocked) | Delayed | 70% |  | Target Date (TBD) | Mustafa Al-Awami | High | Tenant Financing (E1). Required approvals: Central Bank NOC pending. Upcoming: Change Request Development; Obtaining NOC. Bank advised that change-request development will proceed only after Wasl obtains its license and the bank obtains Central Bank NOC. [Date anomaly corrected: business-analysis target year 2024 -> 2025] | - | 2026-07-08 | High
PRD-004 | Product/Integration | BANK-002 | Al Rajhi Bank | مصرف الراجحي | E1 | Testing / Obtaining NOC (blocked) | Delayed | 60% |  | Target Date (TBD) | Ismail Al-Qahtani; Majed Al-Omran | High | Tenant Financing (E1). Required approvals: Central Bank NOC pending. Upcoming: Testing; Obtaining NOC. Bank advised pre-launch testing will start only after the bank obtains its Central Bank NOC. [Date anomaly corrected: business-analysis target year 2024 -> 2025] | - | 2026-07-08 | High
PRD-005 | Product/Integration | BANK-005 | Alinma Bank | مصرف الإنماء | S3 | Agreement | In Progress | 20% | 2026-07-07 | Target Date | Mustafa Al-Awami | Medium | Product S3. Required approvals: Central Bank NOC pending. Upcoming: Agreement; Business Analysis; Technical Development; Testing; Obtaining NOC. Working on contract signature to start work. | - | 2026-07-08 | High
PRD-006 | Product/Integration | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | S3 | Business Analysis | In Progress | 40% | 2026-07-10 | Target Date | Mustafa Al-Awami; Badr Al-Sahli | Medium | Product S3. Required approvals: Central Bank NOC pending. Upcoming: Business Analysis; Technical Development; Testing; Obtaining NOC. Business analysis underway. [Bank name standardized from 'Al Ahli Bank' to Saudi National Bank (SNB)] | - | 2026-07-08 | Medium
PRD-007 | Product/Integration | BANK-002 | Al Rajhi Bank | مصرف الراجحي | S3 | Agreement / Business Analysis | Delayed | 20% | 2026-04-30 | Target Date | Ismail Al-Qahtani; Majed Al-Omran | High | Product S3. Required approvals: -. Upcoming: Agreement; Business Analysis; Technical Development; Testing. Agreement under legal review at the bank; requirements-analysis meeting held. Target dates have passed - flagged as delayed. | - | 2026-07-08 | High
PRD-008 | Product/Integration | BANK-011 | STC Bank | بنك STC | E1 | Opportunity Study & Bank Presentation | Delayed | 10% | 2026-05-30 | Target Date | Wasl Partnerships Team | High | Tenant Financing (E1). Required approvals: -. Upcoming: Opportunity Study & Presentation; Business Analysis; Technical Development; Testing. Awaiting bank response. [Date format corrected from 05/30/2026 to 30/05/2026 - target date has passed] | - | 2026-07-08 | High
PRD-009 | Product/Integration | BANK-012 | D360 Bank | D360 Bank | E1 | Opportunity Study & Bank Presentation | In Progress | 5% | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Tenant Financing (E1). Required approvals: -. Upcoming: Opportunity Study & Presentation; Business Analysis; Technical Development; Testing. Agreement and required documents shared; awaiting bank response. | - | 2026-07-08 | Medium
PRD-010 | Product/Integration | BANK-027 | Raize | رايز | E1 | Agreement | Delayed | 5% | 2026-04-30 | Target Date | Wasl Partnerships Team | High | Tenant Financing (E1). Required approvals: -. Upcoming: Agreement; Business Analysis; Technical Development; Testing. Agreement under legal review at the bank. [Date format corrected from 04/30/2026 to 30/04/2026 - target date has passed] | - | 2026-07-08 | High
PRD-011 | Product/Integration | BANK-005 | Alinma Bank | مصرف الإنماء | E1 | Agreement | In Progress | 5% | 2026-07-10 | Target Date | Mustafa Al-Awami | Medium | Tenant Financing (E1). Required approvals: Central Bank NOC pending. Upcoming: Agreement; Business Analysis; Technical Development; Testing; Obtaining NOC. Agreement under legal review at the bank. | - | 2026-07-08 | Medium
PRD-012 | Product/Integration | BANK-009 | Arab National Bank (ANB) | البنك العربي الوطني | E1 | Technical Development (pending internal coordination) | In Progress | 20% | 2026-06-29 | Target Date | Mustafa Al-Awami | Medium | Tenant Financing (E1). Required approvals: -. Upcoming: Technical Development; Testing. Bank requested time to coordinate internally before technical development; NOC already obtained. | - | 2026-07-08 | High
PRD-013 | Product/Integration | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | E1 | Business Analysis | Delayed | 20% | 2026-05-30 | Target Date | Mustafa Al-Awami; Badr Al-Sahli | High | Tenant Financing (E1). Required approvals: Central Bank NOC pending. Upcoming: Business Analysis; Technical Development; Testing; Obtaining NOC. [Target date has passed - flagged as delayed] | - | 2026-07-08 | High
PRD-014 | Product/Integration | BANK-028 | Manafea | منافع | E2 | Agreement / Business Analysis | In Progress | 10% | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Product E2. Required approvals: Central Bank NOC pending. Upcoming: Agreement; Business Analysis; Technical Development; Testing; Obtaining NOC. Agreement under legal review at the entity; requirements-analysis meeting held. | - | 2026-07-08 | Medium
PRD-015 | Product/Integration | BANK-029 | Barq | برق | E1 | Opportunity Study & Presentation to Financing Entity | Not Started | 0% |  | Target Date (TBD) | Wasl Partnerships Team | - | Tenant Financing (E1). Required approvals: -. Upcoming: Opportunity Study & Presentation; Agreement Signature; Business Analysis; Testing. Awaiting entity response to the proposed opportunity. | - | 2026-07-08 | Medium
MTG-001 | Meeting | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | Technical integration linkage requirements | Complete |  | 2026-02-16 | Email/Technical Coordination | Ahli team | - | Product/topic context: Tenant Financing. SNB sent required technical linkage email. | - | 2026-07-08
MTG-002 | Meeting | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | NOC request status inquiry | Complete |  | 2026-02-10 | Follow-up Call | Ismail Al-Qahtani / Majed Al-Omran | - | Product/topic context: Tenant Financing. Bank to confirm NOC status by end of day. | - | 2026-07-08
MTG-003 | Meeting | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | NOC status follow-up | Complete |  | 2026-02-12 | Meeting | Ismail Al-Qahtani / Majed Al-Omran | - | Product/topic context: Tenant Financing. Meeting held Thursday 12 Feb. | - | 2026-07-08
MTG-004 | Meeting | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Off-plan financing product concept presentation | Complete |  | 2026-02-18 | Meeting | Wasl Partnerships Team | - | Product/topic context: Off-plan Financing. Concept presented to Al Rajhi Wed 18 Feb. | - | 2026-07-08
MTG-005 | Meeting | BANK-003 | Riyad Bank | بنك الرياض | - | Product E1 status review | Complete |  | 2026-02-12 | Meeting | Mustafa Al-Awami / Eman | - | Product/topic context: Tenant/Off-plan Financing (E1). Rescheduled from failed call attempt on 10 Feb. | - | 2026-07-08
MTG-006 | Meeting | BANK-005 | Alinma Bank | مصرف الإنماء | - | Walkthrough of technical integration document | Complete |  | 2026-02-17 | Meeting | Mustafa Al-Awami | - | Product/topic context: Tenant Financing. Held Tuesday 17 Feb. | - | 2026-07-08
MTG-007 | Meeting | BANK-005 | Alinma Bank | مصرف الإنماء | - | Off-plan financing discussion | Complete |  | 2026-02-10 | Meeting | Wasl Partnerships Team | - | Product/topic context: Off-plan Financing. Rescheduled from Mon 9 Feb (no answer). | - | 2026-07-08
MTG-008 | Meeting | BANK-006 | Saudi Awwal Bank (SAB) | البنك السعودي الأول (ساب) | - | Meeting scheduling for both products | Awaiting Response |  | 2026-02-18 | Follow-up Email | Ismail | - | Product/topic context: Off-plan / Tenant Financing. Awaiting bank response. | - | 2026-07-08
MTG-009 | Meeting | BANK-009 | Arab National Bank (ANB) | البنك العربي الوطني | - | NOC & integration sequencing | Complete |  | 2026-01-19 | Status Update | Mustafa Al-Awami | - | Product/topic context: Tenant Financing. Bank pursuing NOC in parallel track. | - | 2026-07-08
MTG-010 | Meeting | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Requirements analysis meeting | Complete |  | 2026-07-07 | Meeting | Wasl Partnerships Team | - | Product/topic context: Product S3. Held at the bank. | - | 2026-07-08
MTG-011 | Meeting | BANK-028 | Manafea | منافع | - | Requirements analysis meeting | Scheduled |  | 2026-07-15 | Meeting (Planned) | Wasl Partnerships Team | - | Product/topic context: Product E2. Legal review of agreement ongoing in parallel. | - | 2026-07-08
MTG-012 | Meeting | BANK-023 | J-B Finance | جيبي | - | Trial-phase completion follow-up | Complete |  | 2026-02-16 | Follow-up | Wasl Partnerships Team | - | Product/topic context: Tenant Financing (E1). - | - | 2026-07-08
MTG-013 | Meeting | BANK-024 | The Saudi Investment Bank | البنك السعودي للإستثمار | - | Company profile & NDA status | Ongoing |  | 2026-02-19 | Contact | Wasl Partnerships Team | - | Product/topic context: General. Profile to be emailed; NDA status to be checked next. | - | 2026-07-08
MTG-014 | Meeting | BANK-015 | Bidaya Finance | بداية للتمويل | - | Relationship status check-in | Complete |  | 2026-02-02 | Status Update | Wasl Partnerships Team | - | Product/topic context: General. - | - | 2026-07-08
MTG-015 | Meeting | BANK-016 | Nayifat | نايفات | - | Integration progress check-in | Complete |  | 2026-01-28 | Status Update | Wasl Partnerships Team | - | Product/topic context: Tenant Financing (E1). - | - | 2026-07-08
RSK-001 | Risk | BANK-003 | Riyad Bank | بنك الرياض | - | Schedule Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Target date has passed with stage not yet complete. Bank advised that change-request development will proceed only after Wasl obtains its license and the bank obtains Central Bank NOC. [Date anomaly corrected: business-analysis target year 2024 -> 2025] | - | 2026-07-08 | High
RSK-002 | Risk | BANK-003 | Riyad Bank | بنك الرياض | - | Regulatory Dependency | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Progress blocked pending Central Bank (SAMA) NOC to the partner bank. Cannot proceed to next stage until the bank secures its own NOC. | - | 2026-07-08 | High
RSK-003 | Risk | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Schedule Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Target date has passed with stage not yet complete. Bank advised pre-launch testing will start only after the bank obtains its Central Bank NOC. [Date anomaly corrected: business-analysis target year 2024 -> 2025] | - | 2026-07-08 | High
RSK-004 | Risk | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Regulatory Dependency | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Progress blocked pending Central Bank (SAMA) NOC to the partner bank. Cannot proceed to next stage until the bank secures its own NOC. | - | 2026-07-08 | High
RSK-005 | Risk | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Schedule Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | S3 - Product S3: Target date has passed with stage not yet complete. Agreement under legal review at the bank; requirements-analysis meeting held. Target dates have passed - flagged as delayed. | - | 2026-07-08 | High
RSK-006 | Risk | BANK-011 | STC Bank | بنك STC | - | Schedule Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Target date has passed with stage not yet complete. Awaiting bank response. [Date format corrected from 05/30/2026 to 30/05/2026 - target date has passed] | - | 2026-07-08 | High
RSK-007 | Risk | BANK-027 | Raize | رايز | - | Schedule Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Target date has passed with stage not yet complete. Agreement under legal review at the bank. [Date format corrected from 04/30/2026 to 30/04/2026 - target date has passed] | - | 2026-07-08 | High
RSK-008 | Risk | BANK-009 | Arab National Bank (ANB) | البنك العربي الوطني | - | Partner-side Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | Medium | E1 - Tenant Financing (E1): Technical development stalled pending bank's internal team coordination. Bank requested time to coordinate internally before technical development; NOC already obtained. | - | 2026-07-08 | Medium
RSK-009 | Risk | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | Schedule Delay | Open |  | 2026-07-08 | Identified Date | Wasl PMO | High | E1 - Tenant Financing (E1): Target date has passed with stage not yet complete. [Target date has passed - flagged as delayed] | - | 2026-07-08 | High
RSK-010 | Risk | - | Internal - Legal Track | - | - | Governance/Legal | Open |  | 2026-07-08 | Identified Date | Wasl PMO | Medium | Board Formation: Appointment of 5th board member outstanding, pending first-party action. Could delay full board formation and downstream corporate approvals. | - | 2026-07-08 | Medium
RSK-011 | Risk | - | Internal - Legal Track | - | - | Governance/Legal | Open |  | 2026-07-08 | Identified Date | Wasl PMO | Medium | Capital Increase: External auditor approval for capital increase not yet started. No target date defined; recommend assigning owner and due date. | - | 2026-07-08 | Medium
RSK-012 | Risk | - | Internal - Financial System Migration | - | - | Technical/Schedule | Open |  | 2026-07-08 | Identified Date | Wasl PMO | Medium | Phase 2 - System Development: Multiple sub-workstreams only partially complete (tax accounts 80%, Sadad accounts 20%, reconciliations 20%). Monitor completion against Aug 2026 live-environment target. | - | 2026-07-08 | Medium
RSK-013 | Risk | - | Multiple Banks (STC, Raize, Alinma-E1) | - | - | Partner Responsiveness | Open |  | 2026-07-08 | Identified Date | Wasl PMO | Medium | Various (E1/Agreement stages): Several partner banks not responding within expected timelines (STC Bank, Raize, off-plan/agreement tracks). Recommend escalation call/email cadence for non-responsive partners. | - | 2026-07-08 | Medium
ACT-001 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | In Progress |  | 2025-11-30 | Due Date | Wasl Legal & First Party | High | Formation of the company's new Board of Directors. 4 of 5 members approved; awaiting remaining updates from the first party regarding appointment of the 5th member. | - | 2026-07-08
ACT-002 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | In Progress |  | 2026-02-15 | Due Date | Wasl Legal & First Party | High | Approval of the company's Bylaws. Bylaws shared with the first party and currently under review. | - | 2026-07-08
ACT-003 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | In Progress |  | 2025-10-30 | Due Date | Wasl Legal & First Party | High | Transfer of first party's cash contribution. Board approved the share-purchase decision; request submitted to Finance for payment-schedule review. | - | 2026-07-08
ACT-004 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | Complete |  | 2025-11-13 | Due Date | Wasl Legal & First Party | Low | Commercial Registration conversion procedures. Company converted to a Simplified Joint Stock Company on 18/12/2025. | - | 2026-07-08
ACT-005 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | Not Started |  |  | Due Date (TBD) | Wasl Legal & First Party | High | External auditor approval for capital increase. Not yet started. | - | 2026-07-08
ACT-006 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | Complete |  | 2026-02-02 | Due Date | Wasl Legal & First Party | Low | Capital increase. Paid-up capital increase to SAR 2,000,000 accepted, as required by the Central Bank. | - | 2026-07-08
ACT-007 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | Complete |  | 2025-09-02 | Due Date | Wasl Legal & First Party | Low | Finalizing addenda procedures. Addenda process completed. | - | 2026-07-08
ACT-008 | Action Item | - | Internal - Legal Track | - | - | Legal / Corporate | In Progress |  | 2026-02-10 | Due Date | Wasl Legal & First Party | High | Signing & approval of addenda by both parties. Addenda provided to the first party. | - | 2026-07-08
ACT-009 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-08-03 | Due Date | Wasl / SecureEyes / NHCI | Low | Obtain SAMA initial approval. Approval obtained on 3 Aug 2025. | - | 2026-07-08
ACT-010 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-08-24 | Due Date | Wasl / SecureEyes / NHCI | Low | Appoint specialized consulting firm (SecureEyes) to prepare SAMA requirements. SecureEyes appointed to complete requirements. | - | 2026-07-08
ACT-011 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-09-22 | Due Date | Wasl / SecureEyes / NHCI | Low | Conduct cyber-security testing on the platform. Report obtained from NHCI. | - | 2026-07-08
ACT-012 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-10-02 | Due Date | Wasl / SecureEyes / NHCI | Low | Prepare company cyber-security policies. | - | 2026-07-08
ACT-013 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-10-02 | Due Date | Wasl / SecureEyes / NHCI | Low | Prepare financial-governance / AML / anti-fraud policies. | - | 2026-07-08
ACT-014 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-10-05 | Due Date | Wasl / SecureEyes / NHCI | Low | Develop technical cyber-security requirements aligned to SAMA. | - | 2026-07-08
ACT-015 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2025-10-20 | Due Date | Wasl / SecureEyes / NHCI | Low | Prepare license application file & SAMA visit. License application file submitted to SAMA. | - | 2026-07-08
ACT-016 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2026-03-10 | Due Date | Wasl / SecureEyes / NHCI | Low | Respond to Central Bank inquiries. Responded to SAMA inquiries on 10 Mar 2026. | - | 2026-07-08
ACT-017 | Action Item | - | Internal - SAMA License | - | - | Regulatory | Complete |  | 2026-06-25 | Due Date | Wasl / SecureEyes / NHCI | Low | Licensing visit. Wasl office readiness for security & safety requirements completed as part of the licensing visit. | - | 2026-07-08
ACT-018 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-02-10 | Due Date | Wasl | Medium | Requirements gathering. - | - | 2026-07-08
ACT-019 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-02-12 | Due Date | Wasl | Medium | Analysis phase. - | - | 2026-07-08
ACT-020 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-02-16 | Due Date | Wasl | Medium | BRD - initial draft. - | - | 2026-07-08
ACT-021 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-02-16 | Due Date | NHCI | Medium | BRD - initial draft approval. - | - | 2026-07-08
ACT-022 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-02-23 | Due Date | Wasl | Medium | BRD - final version. - | - | 2026-07-08
ACT-023 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-02-24 | Due Date | NHCI | Medium | BRD - final version approval. - | - | 2026-07-08
ACT-024 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  |  | Due Date (TBD) | Wasl | Medium | System development. - | - | 2026-07-08
ACT-025 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | Complete |  | 2026-03-30 | Due Date | Wasl | Medium | Services catalogue. - | - | 2026-07-08
ACT-026 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | In Progress |  |  | Due Date (TBD) | NHCI | Medium | API integration. - | - | 2026-07-08
ACT-027 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | In Progress |  |  | Due Date (TBD) | Wasl / NHCI | Medium | Testing. - | - | 2026-07-08
ACT-028 | Action Item | - | Internal - Damen Account | - | - | Product / Integration | In Progress |  |  | Due Date (TBD) | Wasl / NHCI | Medium | Launch. - | - | 2026-07-08
ACT-029 | Action Item | - | Internal - Financial System Migration | - | - | Systems / Finance | Complete |  | 2026-04-26 | Due Date | Wasl Finance/IT | High | Phase 1 - Assessment & Preparation. Window: Feb - Apr 2026. Current-system & structure review; risk identification; work plan; dev environment setup; bank/tax account data scoping (all within 24 Feb - 26 Apr window, prior to report date). | - | 2026-07-08
ACT-030 | Action Item | - | Internal - Financial System Migration | - | - | Systems / Finance | In Progress |  | 2026-08-15 | Due Date | Wasl Finance/IT | High | Phase 2 - New System Setup & Development. Window: Mar - Aug 2026. Technical environment, test-env links & payment-page links, multi bank-account dev, multi tax-account dev (80%), multi Sadad payment-account dev (20%), server provisioning, live-environment prep (15 Jul-15 Aug), external integrations (banking / payment gateway / Sadad), financial reconciliations (20%). | - | 2026-07-08
ACT-031 | Action Item | - | Internal - Financial System Migration | - | - | Systems / Finance | In Progress |  | 2026-05-31 | Due Date | Wasl Finance/IT | High | Phase 3 - Data & Initiative Migration. Window: May 2026. Migrate all initiative data to the new system and validate accuracy (15-30 May); transfer initiatives to the new bank account (31 May). In-scope: Sakani, Digitar, Real-estate brokerage, Real-estate data, Baladi, Baladi classification, Mustadam. Deferred to later: Faraz, Malak, SupplyPro, Wafi, Ejar. | - | 2026-07-08
ACT-032 | Action Item | - | Internal - Financial System Migration | - | - | Systems / Finance | Complete |  | 2026-06-11 | Due Date | Wasl Finance/IT | High | Phase 4 - Testing (UAT). Window: May - Jun 2026. User Acceptance Testing execution and resolution of issues prior to final sign-off (31 May - 11 Jun). | - | 2026-07-08
ACT-033 | Action Item | - | Internal - Financial System Migration | - | - | Systems / Finance | Complete |  | 2026-06-14 | Due Date | Wasl Finance/IT | High | Phase 5 - Launch & Full Operation. Window: May - Jun 2026. Data migration, balance migration, activate new / deactivate old links, payment-gateway migration (12 May-13 Jun), Go-Live on 14 Jun 2026. | - | 2026-07-08
ACT-034 | Action Item | BANK-003 | Riyad Bank | بنك الرياض | - | Partner Follow-up | Open |  |  | Due Date (TBD) | Mustafa Al-Awami | High | Follow up on Obtaining NOC / Change Request Development (blocked) for E1 (Tenant Financing (E1)). Bank advised that change-request development will proceed only after Wasl obtains its license and the bank obtains Central Bank NOC. [Date anomaly corrected: business-analysis target year 2024 -> 2025] | - | 2026-07-08
ACT-035 | Action Item | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Partner Follow-up | Open |  |  | Due Date (TBD) | Ismail Al-Qahtani; Majed Al-Omran | High | Follow up on Testing / Obtaining NOC (blocked) for E1 (Tenant Financing (E1)). Bank advised pre-launch testing will start only after the bank obtains its Central Bank NOC. [Date anomaly corrected: business-analysis target year 2024 -> 2025] | - | 2026-07-08
ACT-036 | Action Item | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Partner Follow-up | Open |  | 2026-04-30 | Due Date | Ismail Al-Qahtani; Majed Al-Omran | High | Follow up on Agreement / Business Analysis for S3 (Product S3). Agreement under legal review at the bank; requirements-analysis meeting held. Target dates have passed - flagged as delayed. | - | 2026-07-08
ACT-037 | Action Item | BANK-011 | STC Bank | بنك STC | - | Partner Follow-up | Open |  | 2026-05-30 | Due Date | Wasl Partnerships Team | High | Follow up on Opportunity Study & Bank Presentation for E1 (Tenant Financing (E1)). Awaiting bank response. [Date format corrected from 05/30/2026 to 30/05/2026 - target date has passed] | - | 2026-07-08
ACT-038 | Action Item | BANK-012 | D360 Bank | D360 Bank | - | Partner Follow-up | Open |  | 2026-07-15 | Due Date | Wasl Partnerships Team | Medium | Follow up on Opportunity Study & Bank Presentation for E1 (Tenant Financing (E1)). Agreement and required documents shared; awaiting bank response. | - | 2026-07-08
ACT-039 | Action Item | BANK-027 | Raize | رايز | - | Partner Follow-up | Open |  | 2026-04-30 | Due Date | Wasl Partnerships Team | High | Follow up on Agreement for E1 (Tenant Financing (E1)). Agreement under legal review at the bank. [Date format corrected from 04/30/2026 to 30/04/2026 - target date has passed] | - | 2026-07-08
ACT-040 | Action Item | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | Partner Follow-up | Open |  | 2026-05-30 | Due Date | Mustafa Al-Awami; Badr Al-Sahli | High | Follow up on Business Analysis for E1 (Tenant Financing (E1)). [Target date has passed - flagged as delayed] | - | 2026-07-08
ACT-041 | Action Item | BANK-029 | Barq | برق | - | Partner Follow-up | Open |  |  | Due Date (TBD) | Wasl Partnerships Team | Medium | Follow up on Opportunity Study & Presentation to Financing Entity for E1 (Tenant Financing (E1)). Awaiting entity response to the proposed opportunity. | - | 2026-07-08
DDL-001 | Deadline | BANK-002 | Al Rajhi Bank | مصرف الراجحي | S3 | Agreement | OVERDUE |  | 2026-04-30 | Target Date | Wasl Partnerships Team | High | Product S3. Stage status: In Progress. Days from today: -69. Under legal review at the bank | - | 2026-07-08
DDL-002 | Deadline | BANK-027 | Raize | رايز | E1 | Agreement | OVERDUE |  | 2026-04-30 | Target Date | Wasl Partnerships Team | High | Tenant Financing (E1). Stage status: In Progress. Days from today: -69. Under legal review at the bank | - | 2026-07-08
DDL-003 | Deadline | BANK-011 | STC Bank | بنك STC | E1 | Opportunity Study & Presentation | OVERDUE |  | 2026-05-30 | Target Date | Wasl Partnerships Team | High | Tenant Financing (E1). Stage status: In Progress. Days from today: -39. Awaiting bank response | - | 2026-07-08
DDL-004 | Deadline | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | E1 | Business Analysis | OVERDUE |  | 2026-05-30 | Target Date | Wasl Partnerships Team | High | Tenant Financing (E1). Stage status: In Progress. Days from today: -39. TBD | - | 2026-07-08
DDL-005 | Deadline | BANK-005 | Alinma Bank | مصرف الإنماء | S3 | Agreement | OVERDUE |  | 2026-07-07 | Target Date | Wasl Partnerships Team | High | Product S3. Stage status: In Progress. Days from today: -1. Working on signing contracts to start work | - | 2026-07-08
DDL-006 | Deadline | BANK-002 | Al Rajhi Bank | مصرف الراجحي | S3 | Business Analysis | OVERDUE |  | 2026-07-07 | Target Date | Wasl Partnerships Team | High | Product S3. Stage status: In Progress. Days from today: -1. Meeting held to analyze requirements at the bank | - | 2026-07-08
DDL-007 | Deadline | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | S3 | Business Analysis | Due Soon |  | 2026-07-10 | Target Date | Wasl Partnerships Team | Medium | Product S3. Stage status: In Progress. Days from today: 2. Business analysis started | - | 2026-07-08
DDL-008 | Deadline | BANK-005 | Alinma Bank | مصرف الإنماء | E1 | Agreement | Due Soon |  | 2026-07-10 | Target Date | Wasl Partnerships Team | Medium | Tenant Financing (E1). Stage status: In Progress. Days from today: 2. Under legal review at the bank | - | 2026-07-08
DDL-009 | Deadline | BANK-023 | J-B Finance | جيبي | E1 | Testing | Due Soon |  | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Tenant Financing (E1). Stage status: In Progress. Days from today: 7. TBD | - | 2026-07-08
DDL-010 | Deadline | BANK-012 | D360 Bank | D360 Bank | E1 | Opportunity Study & Presentation | Due Soon |  | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Tenant Financing (E1). Stage status: In Progress. Days from today: 7. Awaiting bank response | - | 2026-07-08
DDL-011 | Deadline | BANK-028 | Manafea | منافع | E2 | Agreement | Due Soon |  | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Product E2. Stage status: In Progress. Days from today: 7. Under legal review at the entity | - | 2026-07-08
DDL-012 | Deadline | BANK-028 | Manafea | منافع | E2 | Business Analysis | Due Soon |  | 2026-07-15 | Target Date | Wasl Partnerships Team | Medium | Product E2. Stage status: In Progress. Days from today: 7. Meeting held to analyze requirements at the entity | - | 2026-07-08
DOC-001 | Document | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.snb.com.sa | - | 2026-07-08
DOC-002 | Document | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA done; Integration & Negotiation PENDING | - | 2026-07-08
DOC-003 | Document | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.alrajhibank.com.sa | - | 2026-07-08
DOC-004 | Document | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA done; Integration & Negotiation PENDING | - | 2026-07-08
DOC-005 | Document | BANK-003 | Riyad Bank | بنك الرياض | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.riyadbank.com | - | 2026-07-08
DOC-006 | Document | BANK-003 | Riyad Bank | بنك الرياض | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA, Integration, Negotiation all Y (most advanced pipeline) | - | 2026-07-08
DOC-007 | Document | BANK-004 | Banque Saudi Fransi (BSF) | البنك السعودي الفرنسي | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.alfransi.com | - | 2026-07-08
DOC-008 | Document | BANK-004 | Banque Saudi Fransi (BSF) | البنك السعودي الفرنسي | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA done; Integration not started | - | 2026-07-08
DOC-009 | Document | BANK-005 | Alinma Bank | مصرف الإنماء | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.alinma.com | - | 2026-07-08
DOC-010 | Document | BANK-005 | Alinma Bank | مصرف الإنماء | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA done; Integration & Negotiation PENDING | - | 2026-07-08
DOC-011 | Document | BANK-006 | Saudi Awwal Bank (SAB) | البنك السعودي الأول (ساب) | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.sab.com.sa | - | 2026-07-08
DOC-012 | Document | BANK-006 | Saudi Awwal Bank (SAB) | البنك السعودي الأول (ساب) | - | NDA | Pending |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo done; NDA PENDING | - | 2026-07-08
DOC-013 | Document | BANK-007 | Albilad Bank | بنك البلاد | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.bankalbilad.com.sa | - | 2026-07-08
DOC-014 | Document | BANK-008 | Aljazira Bank | بنك الجزيرة | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.bankaljazira.com.sa | - | 2026-07-08
DOC-015 | Document | BANK-009 | Arab National Bank (ANB) | البنك العربي الوطني | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.anb.com.sa | - | 2026-07-08
DOC-016 | Document | BANK-009 | Arab National Bank (ANB) | البنك العربي الوطني | - | NDA | Pending |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo done; NDA PENDING | - | 2026-07-08
DOC-017 | Document | BANK-010 | Gulf International Bank (GIB) | بنك الخليج الدولي | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.gibl.com | - | 2026-07-08
DOC-018 | Document | BANK-011 | STC Bank | بنك STC | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.stcbank.com.sa | - | 2026-07-08
DOC-019 | Document | BANK-012 | D360 Bank | D360 Bank | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.d360bank.com | - | 2026-07-08
DOC-020 | Document | BANK-013 | Saudi Finance Company (SFC) | الشركة السعودية للتمويل | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://sfco.com.sa | - | 2026-07-08
DOC-021 | Document | BANK-014 | Abdul Latif Jameel Finance | عبد اللطيف جميل للتمويل | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.alj.com | - | 2026-07-08
DOC-022 | Document | BANK-015 | Bidaya Finance | بداية للتمويل | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.bidaya.com.sa | - | 2026-07-08
DOC-023 | Document | BANK-015 | Bidaya Finance | بداية للتمويل | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA done | - | 2026-07-08
DOC-024 | Document | BANK-016 | Nayifat | نايفات | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://nayifat.com.sa | - | 2026-07-08
DOC-025 | Document | BANK-017 | Yanal | يانال | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.saudi-orix.com | - | 2026-07-08
DOC-026 | Document | BANK-018 | Al Yusr | اليسر للتمويل | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.alyusr.com.sa | - | 2026-07-08
DOC-027 | Document | BANK-018 | Al Yusr | اليسر للتمويل | - | NDA | Signed |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo, NDA done | - | 2026-07-08
DOC-028 | Document | BANK-019 | AJIL Financial Services | أجل للخدمات المالية | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://ajil.com.sa | - | 2026-07-08
DOC-029 | Document | BANK-020 | Kirnaf Finance | كِرنف للتمويل | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.kirnaf.com | - | 2026-07-08
DOC-030 | Document | BANK-021 | Matager | مطاجر | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.matager.sa | - | 2026-07-08
DOC-031 | Document | BANK-022 | Saudi Real Estate Refinance Co. (SRC) | شركة التمويل العقاري السعودية | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.src.com.sa | - | 2026-07-08
DOC-032 | Document | BANK-023 | J-B Finance | جيبي | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://j-b.com.sa/en/ | - | 2026-07-08
DOC-033 | Document | BANK-024 | The Saudi Investment Bank | البنك السعودي للإستثمار | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.saib.com.sa/ar | - | 2026-07-08
DOC-034 | Document | BANK-024 | The Saudi Investment Bank | البنك السعودي للإستثمار | - | NDA | Pending |  |  | - | Wasl Partnerships Team | - | Initial Contact, Presentation, Demo done; NDA PENDING | - | 2026-07-08
DOC-035 | Document | BANK-025 | Tamara | تمارا | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://tamara.co/ar-sa | - | 2026-07-08
DOC-036 | Document | BANK-026 | Emkan | إمكان | - | Official Website | Available |  |  | - | Wasl Partnerships Team | - | https://www.emkanfinance.com.sa/ | - | 2026-07-08
DOC-037 | Document | BANK-001 | Saudi National Bank (SNB) | البنك الأهلي السعودي | - | Technical Integration Linkage Document | Available |  |  | - | Wasl Partnerships Team | - | Sent by SNB Mon 16 Feb 2026. | - | 2026-07-08
DOC-038 | Document | BANK-004 | Banque Saudi Fransi (BSF) | البنك السعودي الفرنسي | - | Company Profile Deck | In Review |  |  | - | Wasl Partnerships Team | - | Wasl profile being refreshed; awaiting final version to send. | - | 2026-07-08
DOC-039 | Document | BANK-024 | The Saudi Investment Bank | البنك السعودي للإستثمار | - | Company Profile Deck | Pending |  |  | - | Wasl Partnerships Team | - | To be emailed to Sultan Al-Khamis. | - | 2026-07-08
DOC-040 | Document | BANK-012 | D360 Bank | D360 Bank | - | Agreement + Supporting Documents | Pending |  |  | - | Wasl Partnerships Team | - | Shared with the bank; response pending. | - | 2026-07-08
DOC-041 | Document | BANK-027 | Raize | رايز | - | Agreement | In Review |  |  | - | Wasl Partnerships Team | - | - | - | 2026-07-08
DOC-042 | Document | BANK-005 | Alinma Bank | مصرف الإنماء | - | Agreement (Product E1) | In Review |  |  | - | Wasl Partnerships Team | - | - | - | 2026-07-08
DOC-043 | Document | BANK-002 | Al Rajhi Bank | مصرف الراجحي | - | Agreement (Product S3) | In Review |  |  | - | Wasl Partnerships Team | - | - | - | 2026-07-08
DOC-044 | Document | BANK-028 | Manafea | منافع | - | Agreement (Product E2) | In Review |  |  | - | Wasl Partnerships Team | - | - | - | 2026-07-08
DOC-045 | Document | - | Internal - Legal Track | - | - | Company Bylaws (النظام الأساس) | In Review |  |  | - | Wasl Partnerships Team | - | - | - | 2026-07-08
DOC-046 | Document | - | Internal - Legal Track | - | - | Addenda (الملاحق) | Pending |  |  | - | Wasl Partnerships Team | - | - | - | 2026-07-08
DOC-047 | Document | - | Internal - SAMA License | - | - | License Application File | In Review |  |  | - | Wasl Partnerships Team | - | Submitted 20 Oct 2025. | - | 2026-07-08
DOC-048 | Document | - | Internal - Damen Account | - | - | Business Requirements Document (BRD) | Approved |  |  | - | Wasl Partnerships Team | - | Approved by NHCI 24 Feb 2026. | - | 2026-07-08